## Task List
Task | Estimated Effort (man*hour) | Actual Effort (man*hour) | Start Date | Finish Date | Owner | Status(%) | Comments
Aug 3-Aug 7
Orchard框架搭建 | 16 |  | 2015-08-03 | 2015-08-04 | Frank | Finished
WeChat集成 | 8 |  | 2015-08-05 | 2015-08-05 | Frank | Finished
IVote集成调查 | 16 |  | 2015-08-06 | 2015-08-07 | Frank | Finished
环境熟悉及SSO调试 | 24 |  | 2015-08-05 | 2015-08-07 | Sean | Finished
Aug 10-Aug 14
云服务器调试发布 | 16 |  | 2015-08-10 | 2015-08-11 | Frank | Finished
微信平台调试及更能添加 | 16 |  | 2015-08-12 | 2015-08-13 | Frank | Finished
Ivote调试 | 8 |  | 2015-08-14 | 2015-08-14 | Frank | Finished
后台-发消息选择应用页面 | 8 |  | 2015-08-10 | 2015-08-10 | Chao | Finished
后台-发送文字页面 | 16 |  | 2015-08-11 | 2015-08-12 | Chao | Finished
后台-发送图文页面 | 16 |  | 2015-08-13 | 2015-08-14 | Chao | Finished
后台-发送消息预览功能 | 24 |  | 2015-08-10 | 2015-08-11 | Max | Finished
后台-微信接口调试以及获取成员信息 | 8 |  | 2015-08-12 | 2015-08-13 | Max | Finished
SSO调试 | 8 |  | 2015-08-13 | 2015-08-14 | Sean | Finished
Aug 17-Aug 21
后台-消息中心（用户消息，应用消息） | 24 |  | 2015-08-19 | 2015-08-21 | Sean | Finished
后台-发送图片页面 | 16 |  | 2015-08-17 | 2015-08-18 | Chao | Finished
后台-表情包以及富文本 | 8 |  | 2015-08-19 | 2015-08-19 | Chao | Finished
后台-发送范围 | 16 |  | 2015-08-20 | 2015-08-21 | Chao | Finished
后台-微信预览、上传图片 | 16 |  | 2015-08-17 | 2015-08-18 | Max | Finished
后台-保密消息、永久保存功能 | 8 |  | 2015-08-19 | 2015-08-19 | Max | Finished
新闻列表页面 | 8 |  | 2015-08-20 | 2015-08-20 | Frank | Finished
新闻详情页面 | 8 |  | 2015-08-21 | 2015-08-21 | Frank | Finished
Aug 24-Aug 28
测试系统发布 | 8 |  | 2015-08-24 | 2015-08-24 | Frank | Finished
新闻列表页面数据绑定以及下拉加载 | 8 |  | 2015-08-26 | 2015-08-26 | Frank | Finished
Ivote样式修改 | 8 |  | 2015-08-27 | 2015-08-27 | Frank | Finished
Ivote登录方式以及权限修改 | 8 |  | 2015-08-28 | 2015-08-28 | Frank | Finished
后台-发送消息整合调试 | 24 |  | 2015-08-24 | 2015-08-26 | Chao | Finished
后台-测试以及Bug修改 | 16 |  | 2015-08-27 | 2015-08-28 | Chao | Finished
在线调查列表页面 | 8 |  | 2015-08-28 | 2015-08-28 | Sean | Finished
在线调查列表页面 | 8 |  | 2015-08-28 | 2015-08-28 | Sean | Finished
我的反馈功能实现 | 8 |  | 2015-08-28 | 2015-08-28 | Sean | Finished
Aug 31-Sep 6
在线调查以及在线问卷页面样式修改 | 8 |  | 2015-08-31 | 2015-08-31 | Chao | Finished
我的反馈样式及功能修改 | 8 |  | 2015-09-01 | 2015-09-01 | Chao | Finished
前后台Bug修改 | 16 |  | 2015-09-02 | 2015-09-06 | Chao | Finished
SSO | 8 |  | 2015-09-06 | 2015-09-06 | Sean | Pending
不能分享功能，GPS | 16 |  | 2015-08-31 | 2015-09-01 | Frank | Finished
权限验证（非可见范围用户不能查看任何内容） | 16 |  | 2015-09-02 | 2015-09-06 | Frank | Finished
Sep 7-Sep 11
前后台Bug修改 | 32 |  | 2015-09-07 | 2015-09-09 | Chao | Finished
测试内容清理 | 8 |  | 2015-09-09 | 2015-09-09 | Frank | Finished
系统发布 | 8 |  | 2015-09-10 | 2015-09-10 | Frank | Finished
系统测试 | 16 |  | 2015-09-09 | 2015-09-10 | Daisy | Finished
Sep 14-Sep 18
前后台Bug修改 | 16 |  | 2015-09-14 | 2015-09-15 | Chao
系统发布 | 8 |  | 2015-09-15 | 2015-09-15 | Frank
系统测试 | 8 |  | 2015-09-16 | 2015-09-16 | Daisy